## Activity Control
EXL HACKATHON 2024
Company Name | EXL | [44 empty] | Phase 1 | 2024-06-14
Project Lead | ALEJANDRO G. |  | Project Start: | 2024-05-20 | [41 empty] | Phase 2 | 2024-06-29
|  |  | Display: | Daily | [41 empty] | Phase 3 | 2024-07-09
|  |  | Display Period: | 1
[10 empty] | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23
TASK | LEAD | CLR | PROGRESS | START | END | WORK DAYS | CAL DAYS | DAYS DONE | DAYS LEFT | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | EXPECTED OUTCOME
Team Formation |  | - | 100% |  | - | - | 0 | 0 | 0
Discuss individual strengths | Alejandro G. | G | 100% | 2024-05-20 | 2024-05-21 | 2 | 2 | 2 | 0 | [35 empty] | Identification and documentation of reliable data sources
Identify interests | Alejandro G. | G | 100% | 2024-05-20 | 2024-05-21 | 2 | 2 | 2 | 0 | [35 empty] | Understand each member's interests to align tasks with their passions
Determine availability | Alejandro G. | G | 100% | 2024-05-20 | 2024-05-21 | 2 | 2 | 2 | 0 | [35 empty] | Confirm each member's availability to ensure effective collaboration and task management
Data Exploration and Preprocessing |  | - | 100% |  | - | - | 0 | 0 | 0
Research for reliable data sources | All Team | Y | 100% | 2024-05-21 | 2024-05-21 | 1 | 1 | 1 | 0 | [35 empty] | Comprehensive list of additional reliable data sources
Data Collection | Alejandro & Alondra | P | 100% | 2024-05-21 | 2024-05-22 | 2 | 2 | 2 | 0 | [35 empty] | Matches, Leagues, and Teams databases extracted
Standarized Formats | Alejandro G. | G | 100% | 2024-05-22 | 2024-05-23 | 2 | 2 | 2 | 0 | [35 empty] | Uniform structure for all data entries, ensuring consistency across different databases
Cleaned Data | Alejandro G. | G | 100% | 2024-05-22 | 2024-05-23 | 2 | 2 | 2 | 0 | [35 empty] | Removal of duplicates, inconsistencies, and irrelevant information to improve data quality
Merged Datasets | Alejandro G. | G | 100% | 2024-05-23 | 2024-05-24 | 2 | 2 | 2 | 0 | [35 empty] | Integration of matches, leagues, and teams data into a cohesive dataset, enabling comprehensive analysis
Feature Engineering | Alejandro G. | G | 100% | 2024-05-24 | 2024-05-29 | 4 | 6 | 6 | 0 | [35 empty] | Creation of new features (e.g., average goals per match, win/loss ratios) that enhance the dataset's analytical value
Data Enrichment | Alejandro & Alondra | P | 100% | 2024-05-24 | 2024-05-29 | 4 | 6 | 6 | 0 | [35 empty] | Addition of contextual information such as match location, weather conditions, and historical performance metrics
Indexed Data | Jesus & Oscar | A | 100% | 2024-05-24 | 2024-05-29 | 4 | 6 | 6 | 0 | [35 empty] | Establishment of indexes for faster query performance and data retrieval
Consistent Naming Conventions | Alejandro & Alondra | P | 100% | 2024-05-24 | 2024-05-29 | 4 | 6 | 6 | 0 | [35 empty] | Standardized naming conventions for leagues, teams, and matches to avoid ambiguity
Time-Series Alligment | Alejandro G. | G | 100% | 2024-05-24 | 2024-05-29 | 4 | 6 | 6 | 0 | [35 empty] | Synchronization of time-series data to ensure accurate temporal analysis
Data Collection | Carlos Axel E. | O | 100% | 2024-05-20 | 2024-05-24 | 5 | 5 | 5 | 0 | [35 empty] | Euro 2024 Qualifying matches data (minute by minute) Extraction via txt files
Data Transformation | Carlos Axel E. | O | 100% | 2024-05-27 | 2024-05-29 | 3 | 3 | 3 | 0 | [35 empty] | Import of txt files into python, and rearrange it into a structura that can be handled for modelling
Strikers identification | Jesus & Oscar | A | 100% | 2024-05-20 | 2024-05-21 | 2 | 2 | 2 | 0 | [35 empty] | Identify strikers for every team
Strikers selection | Jesus & Oscar | A | 100% | 2024-05-21 | 2024-05-22 | 2 | 2 | 2 | 0 | [35 empty] | Select striker that are starters and could play in most of the matches
List reduce | Jesus & Oscar | A | 100% | 2024-05-22 | 2024-05-23 | 2 | 2 | 2 | 0 | [35 empty] | Reduce the list of strikers only for the ones that exists enough data to model
Data Collection | Jesus & Oscar | A | 100% | 2024-05-23 | 2024-05-27 | 3 | 5 | 5 | 0 | [35 empty] | Collect historical match record for players
Data Transformation | Jesus & Oscar | A | 100% | 2024-05-27 | 2024-05-28 | 2 | 2 | 2 | 0 | [35 empty] | Transform data into numerical
Data Cleaning | Jesus & Oscar | A | 100% | 2024-05-28 | 2024-05-29 | 2 | 2 | 2 | 0 | [35 empty] | Drop variables that could be correlated and not fit in the model
Creating Structure of the Data | All Team | Y | 100% | 2024-05-28 | 2024-05-29 | 2 | 2 | 2 | 0 | [35 empty] | Stablish the data that is going to be used for the model(s) selection
Model Development and Training |  | - | 37.5% |  | - | - | 0 | 0 | 0
Model(s) selection | All Team | Y | 100% | 2024-05-29 | 2024-05-29 | 1 | 1 | 1 | 0 | [35 empty] | Identify the most suitable machine learning algorithms or SVM model for our project
EDA | All Team | Y | 25% | 2024-05-29 | 2024-06-05 | 6 | 8 | 2 | 6 | [35 empty] | Understand the underlying patterns, distributions, and relationships in your data
Model development | All Team | Y | 25% | 2024-06-05 | 2024-06-07 | 3 | 3 | 0 | 3 | [35 empty] | Develop initial models using the selected algorithms and the insights gained from EDA
Model Validation | All Team | Y | 25% | 2024-06-07 | 2024-06-12 | 4 | 6 | 1 | 5 | [35 empty] | Validate the model by splitting the data into training and validation sets, evaluating the model's performance, and iterating on the development process to improve accuracy and robustness
Train and tune the models | All Team | Y | 25% | 2024-06-07 | 2024-06-12 | 4 | 6 | 1 | 5 | [35 empty] | Optimize the performance of the selected model(s)
Evaluate model performance | All Team | Y | 25% | 0+/07 | 2024-06-13 | - | 0 | 0 | 0 | [35 empty] | Finalize the evaluation of the model(s) and prepare for deployment
Predictions and Submission |  | - | 0% |  | - | - | 0 | 0 | 0
Prepare the submission file for Phase 1 |  | - | 0% | 2024-06-13 | 2024-06-13 | 1 | 1 | 0 | 1 | [35 empty] | A comprehensive submission file for Phase 1, including cleaned data, the final model, predictions, and documentation
Analyze Phase 1 performance and retrain models for Phase 2 |  | - | 0% | 2024-06-13 | 2024-06-17 | 3 | 5 | 0 | 5 | [35 empty] | An analytical report on Phase 1 performance with retrained models based on identified improvements
Generate, review, and finalize predictions for Phase 2 |  | - | 0% | 2024-06-14 | 2024-06-29 | 11 | 16 | 0 | 16 | [35 empty] | Accurate and reviewed predictions for Phase 2, ready for submission
Prepare the submission file for Phase 2 |  | - | 0% | 2024-06-14 | 2024-06-29 | 11 | 16 | 0 | 16 | [35 empty] | A comprehensive submission file for Phase 2, including updated data, retrained models, finalized predictions, and documentation
Analyze Phase 2 performance and retrain models for Phase 3 |  | - | 0% | 2024-07-01 | 2024-07-09 | 7 | 9 | 0 | 9 | [35 empty] | An analytical report on Phase 2 performance with retrained models based on identified improvements
Generate, review, and finalize predictions for Phase 3 |  | - | 0% | 2024-07-11 | 2024-07-09 | -3 | -1 | 0 | -1 | [35 empty] | Accurate and reviewed predictions for Phase 3, ready for submission
Final Presentation Preparation |  | - | 0% |  | - | - | 0 | 0 | 0
Prepare and practice final presentation |  | - | 0% | 2024-07-09 | 2024-07-15 | 5 | 7 | 0 | 7
Insert rows above this line
Show Weekends
Show Overdue

## Settings (hidden)
WEEKEND Option
| Weekend String | 0000011
| Monday | 0
| Tuesday | 0
| Wednesday | 0
| Thursday | 0
| Friday | 0
| Saturday | 1
| Sunday | 1
| Show Weekends | TRUE
COLOR CODING
| Names | Color
| Alejandro G. | G
| Carlos Axel E. | O
| Alondra S. | B
| Oscar E. | C
| Jesus T. | M
| Jesus & Oscar | A
| Alejandro & Alondra | P
| All Team | Y
| Milestone | K
-
| Show Overdue | FALSE

## EXL Hackathon 2024
Stage | Actions | ETA
Team Formation | Discuss individual strengths, interests, and availability | 1 week
Data Exploration and Preprocessing | Familiarize the team with provided data repositories and explore additional relevant data sources (e.g., historical Euro Cup data, player statistics) | 1 week
Coordinate the preprocessing of data (handling missing values, feature engineering, etc.)
Determine relevant features and target variables as a team
Model Development and Training | Discuss and select appropriate machine learning algorithms (e.g., classification, regression, poisso, CLT) | 1-2 weeks
Split data into training and validation sets, train and tune the models, evaluate performance, iterate and refine models as needed
Phase 1 Predictions and Submission | Generate, review, and finalize predictions for Phase 1 using trained models. | 1 week (by 14th June 2024)
Prepare the submission file by the Phase 1 deadline, including: i) Code ii) Predictions for Phase 1 iii) Datasets used (only when asked)
Phase 2 Predictions and Submission | Analyze Phase 1 performance, retrain/fine-tune models based on results, generate predictions for Phase 2, prepare the submission file by the Phase 2 deadline, including: i) Code ii) Predictions for Phase 2 iii) Datasets used (only when asked) | 1 week (by 29th June 2024)
Phase 3 Predictions and Submission | Analyze Phase 2 performance, retrain/fine-tune models based on results, generate predictions for Phase 3, prepare the submission file by the Phase 3 deadline, including: i) Code ii) Predictions for Phase 2 iii) Datasets used (only when asked) | 1 week (by 9th July 2024)
Qualified teams ony: Final Presentation Preparation | Prepare and practice a comprehensive presentation showcasing the approach, models, and strategies if the team qualifies for the final presentation round | 1 week (16th July 2024)
Deliver the final presentation to the judges, representing the team, and await the winner announcement together

## Holidays (hidden)
USA |  | Mexico
Date | Holiday name | Date | Celebration
2024-01-01 | New Year’s Day | 2024-01-01 | New Year's Day Observed
2024-01-16 | Martin Luther King Jr Day | 2024-02-05 | Commemorating February 5th
2024-02-20 | Presidents’ Day | 2024-03-18 | Benito Juarez's Birthday
2024-05-29 | Memorial Day | 2024-05-01 | Labor Day
2024-06-16 | Juneteenth | 2024-06-03 | Presidential Election Observed
2024-07-04 | Independence Day | 2024-07-08 | General Election Day Observed
2024-09-04 | Labor Day | 2024-09-16 | Independence Day Observed
2024-10-09 | Columbus Day | 2024-10-01 | Inauguration Day
2024-11-10 | Veterans’ Day | 2024-11-18 | Revolution Day
2024-11-23 | Thanksgiving | 2024-12-25 | Christmas Day
2024-12-25 | Christmas