## Sheet1
Task | Descripcion | Start date | End date
Strikers identification | Identify strikers for every team. | 2024-05-20 | 2024-05-21
Strikers selection | Select striker that are starters and could play in most of the matches | 2024-05-21 | 2024-05-22
List reduce | Reduce the list of strikers only for the ones that exists enough data to model | 2024-05-22 | 2024-05-23
Data collection | Collect historical match record for players | 2024-05-23 | 2024-05-27
Data transformation | Transform data into numerical | 2024-05-27 | 2024-05-28
Data cleaning | Drop variables that could be correlated and not fit in the model | 2024-05-28 | 2024-05-29
data split (Train, test) | Select train and validate | 2024-05-29 | 2024-05-30
Model selection | Select best fit for the model (regression) | 2024-05-31 | 2024-06-05
Model deployment | Apply model | 2024-06-05 | 2024-06-07
Model accuracy | Check if model results are accurate | 2024-06-07 | 2024-06-10
Make predictions | Make the predictions for the upcoming matches | 2024-06-10 | 2024-06-11
Select top striker | Select the top striker with the model results and submit the form | 2024-06-12 | 2024-06-14